## Gantt Chart
Project Gantt Chart
Apr 15 – May 17, 2026 · Presentation: May 13 · Final Submission: May 17
SHARED GDRIVE LINK |  |  | Wk 1 (Apr 15–19) |  |  |  |  | Wk 2 (Apr 20–26) | [6 empty] | Wk 3 (Apr 27–03) | [6 empty] | Wk 4 (May 04–10) | [6 empty] | Wk 5 (May 11–17)
Task | Owner | Status | W 15 | T 16 | F 17 | S 18 | S 19 | M 20 | T 21 | W 22 | T 23 | F 24 | S 25 | S 26 | M 27 | T 28 | W 29 | T 30 | F 01 | S 02 | S 03 | M 04 | T 05 | W 06 | T 07 | F 08 | S 09 | S 10 | M 11 | T 12 | W 13 | T 14 | F 15 | S 16 | S 17
Group Kick-off Meeting in person | ALL | Done
Individual Dataset Pitch & MDSI Persona | Each Member | Done
Shared Game Plan w Gantt Setup + Sprint 1 tasks | Jivan | Done
Finalize Dataset Selection & Game Plan | ALL | Done
PART 1 SUBMISSION (DEADLINE) | Each Member | Done |  |  |  |  | ◆
Acquire + Clean Dataset | Code Track | Done
Exploratory Data Analysis + 3 Advanced Features | Code Track | Done
Define Design System & Branding | Design & Strategy | Done
Dashboard Wireframes & Storyboard | Design & Strategy | Done
Core Dashboard Build & v1 Deployment | Code Track | Done
Stakeholder “Hat” + Narrative / Call-to-Action | Design & Strategy | Ongoing
FUNCTIONAL PROTOTYPE READY | Code + Design | Done | [24 empty] | ◆
Pitch Script Writing & Slides | Design & Strategy | Not Started
Full Group Rehearsals (×2) | All Members | Not Started
LIVE PERSUASION PITCH | All Members | Not Started | [28 empty] | ◆
Final Dashboard Polish & Responsive Optimisation | Code Track | Not Started
Record 3-min Video Walkthrough | Code + Design | Not Started
Data Dictionary + Credits + Documentation | Code + Analyst | Not Started
Final Group Review & Testing | All Members | Not Started
FINAL PORTFOLIO SUBMISSION | All Members | Not Started | [32 empty] | ◆
LEGEND | Task Bar | Milestone / Deadline | Weekend

## Meeting Minutes
Meeting Minutes | [5 empty] | SHARED GDRIVE LINK
Log each meeting. Link to full notes in Google Docs.
Meeting # | Date | Time | Attendees | Agenda | Action Items / Output | Link to Full Notes
1 | 2026-04-16 | 10:00 | Abhi, Ankita, Gem, Jivan, Ka Yan | Agree on Dataset, Roles, and Game Plan for project | Final agreed data, roles, and game plan | https://docs.google.com/document/d/1f6ls71CfuOYjZYWMhx2zZp1qhVkVmwsVphXSAbWkk_M/edit?usp=sharing
2 | 2026-04-27 | 21:00 | Abhi, Ankita, Gem, Jivan, Ka Yan, Harshi, Ranjan | Work update + Agree on Stakeholder + Dashboard Design Proposal | Finalize on stakeholder -> Mayor Policymaker; Data Viz Team -> Finalize on Dashboard Design and Tableau implementation; Ankita Ka Yan to meet before May 6th Presentation Team -> discuss on story/narrative flow; Jivan to set meeting before May 6th Meet on the 6th 5:30PM (Online)[Time Tentative] -- Dashboard Prototype + Presentation Draft
3 | 2026-05-06 | 22:30 | Abhi, Ankita, Gem, Jivan, Ka Yan, Harshi, Ranjan | Dashboard Update + Presentation and Report Planning | Dashboard Update - Good prototype - BUILDS: Replace insights and recos to KPI names of the dashboard; Potentially use "i" tooltip for metric details - Move around visuals to follow actual story of the project Presentation Update - Gem w slides - Start with dashboard details -> then push to story used from dashboard - Final call-to-action = Adopt the Market Health Score -- as standard for allocating housing grants - Flow: General Problem -> Dashboard Details -> What if (Story) -> Solution: Market Health Score - AI -> Base Template for Presentation -- (Send initial draft by FRI) - Orators: Jivan and Abhi - Presentation Help: Gem and Ranjan Part 3: Data Dictionary - README or Tableau Sheet -> Data Dict + Credits - Video Walkthrough -> Ankita, Harshi, Ka Yan, Ranjan
4
5
6
7
8
9
10

## Dataset Proposals
Dataset Proposals
Each member proposes a dataset. Vote and discuss to select the final one.
Proposed By | Topic | Justification | Data Source | Link to Data Pitch | Top 1 (5 pts) | Top 2 (3 pts) | Top 3 (1 pt)
Ankita Adiveppagouda Patil | BTS Airline On-Time Performance (2024) | Each record in this dataset captures a single flight’s operational details, including timing, origin and destination, delay duration, and attributed delay causes. This provides a strong foundation for analysing airline performance across both time and geography. While the dataset already labels reasons for delays, it does not capture the actual conditions behind those labels. This creates a meaningful opportunity for enrichment by integrating external weather data, which is publicly available and can be linked using flight date and airport location. This makes the integration practical and achievable without requiring complex data pipelines. The dataset also meets the requirements of being data-rich, with multiple dimensions and variables that support deeper analysis beyond simple reporting. By combining operational flight data with weather, the analysis can move from identifying what happened to understanding why it happened, enabling more informed insights into whether delays are driven by environmental factors or system-level inefficiencies. | Main data : https://www.transtats.bts.gov/DL_SelectFields.aspx?gnoyr_VQ=FGJ&QO_fu146_anzr=b0-gvzr | Shared on Teams Chat | Motorcycle Dataset | NSW Rental + Bond | US Housing + Civillian Employment
Abhishek Chopda | New York Motor Vehicle Collisions (2024) | Each row represents a unique crash event and includes crash date, time, borough, ZIP code, and lat/lon coordinates. The enrichment path is particularly strong here because we can join datasets (weather) which is freely accessible making a multi-source join very achievable without complex APIs. Also it ticks all the 'data rich' checkmarks needed for this assignment. It can be combined with the weather data, which will help us answer questions like why the collisions happened? Was it the weather or just bad driving skills etc. | Main data: https://data.cityofnewyork.us/Public-Safety/Motor-Vehicle-Collisions-Crashes/h9gi-nx95/about_data | Shared on Teams Chat | US Housing + Civillian Employment | Motor Vehicle Collision dataset | NSW Rental + Bond Refunds
Ferdinando Jr Enriquez | NSW Transport Opal Entry & Exit Data | Records a monthly number of entries and exits for each train, metro, and light rail stations across Sydney from Oct 2024 to Mar 2026. Can be combined with income per suburb data and train service schedules data to create a narrative that tries to answer whether lower income suburbs are underserved and if stations with less train schedules are done by design or is there a need to improve service within them. | https://opendata.transport.nsw.gov.au/dataset/train-station-entries-and-exits-data |  | Motorcycle Dataset | Train Station Transport Data | Airline Operations Data
Gem He | NSW Rental Bond Analysis | Multiple related tables (bond lodgements, refunds, holdings). Monthly/Quarterly/Annual + Geographical (postcodes) + Housing Types + Rental Market Outcomes | NSW Gov Rental Bond Data https://www.nsw.gov.au/housing-and-construction/rental-forms-surveys-and-data/rental-bond-data | https://docs.google.com/document/d/14_vsvCc-pZ7F9rA4qA7Zwj7DSeCdAPHH1iFARsVt6YM/edit?tab=t.0 | US Housing + Civillian Employment | Motorcycle Dataset | NSW Rental + Bond Refunds
Harshini Prasad | Australian Energy Market (NEM) Price & Demand Dynamics | High-frequency temporal (5-min intervals) and spatial data with fields mapped across all 5 National Electricity Market (NEM) states (NSW, QLD, VIC, SA, TAS). Offers massive temporal depth with monthly historical CSV files available from 1998.( we can use from 2024). Enrichment: join with external data on the SETTLEMENTDATE and REGION. ie since the data is hourly.. We can merge with any | https://www.aemo.com.au/energy-systems/electricity/national-electricity-market-nem/data-nem/aggregated-data |  | US Housing + Civillian Employment | Train Station Transport Data | Australian Energy Market (NEM) data
Ka Yan Cheng | US Housing Affordability Crisis | This dataset clearly shows why homes are hard to afford in the US. Home prices are rising, mortgage rates are high, and jobs affect what people can pay. The data helps decision-makers(Mayor / Urban Planning Committee-for pitch) see the problem, understand why it matters, and explore solutions. The dashboard could include helpful tools like state filters and a slider for testing different mortgage rates. Real monthly data(from Jan 2024 to Feb 2026), spatial (51 states) and temporal (month), enrichment by joining all 4 datasets (housing + unemployment + mortgage rates+ median household income). All datasets downloaded from official US government or institutional sources (Zillow, BLS.gov, FRED,census.gov) | Core: State-Level Median Home Values: https://www.zillow.com/research/data/ Enrich: Civilian Employment & Unemployment by State: https://www.bls.gov/lau/tables.htm, 30-Year Fixed Mortgage Rat: https://fred.stlouisfed.org/series/MORTGAGE30US#Median Household Income by states:https://www2.census.gov/library/publications/2025/demo/acsbr-025.pdf |  | US Housing + Civillian Employment | Motorcycle Dataset | NSW Rental + Bond Refunds
Ranjan Khanal | Australian Climate Analysis & Report | Multiple tables that can be merged. Local domain data useful for publishing/research. Variety of temporal and spatial data for selective objectives. | Bureau of Meteorology https://www.bom.gov.au/climate/data/ |  | US Housing + Civillian Employment | NSW Rental + Bond Refunds | Motorcycle Dataset
Final Dataset Decision
Field | Details
Dataset Name | US Housing + Civilian Employment Dataset
Source / URL | Core: State-Level Median Home Values: https://www.zillow.com/research/data/ Enrich: Civilian Employment & Unemployment by State: https://www.bls.gov/lau/tables.htm, 30-Year Fixed Mortgage Rat: https://fred.stlouisfed.org/series/MORTGAGE30US# Median Household Income by states:https://www2.census.gov/library/publications/2025/demo/acsbr-025.pdf
Reason for Selection | The US Housing Affordability dataset was selected as it offers more complete and detailed data compared to Australian alternatives, with home values, mortgage rates, and employment info readily mergeable to a single dataset. Similarly, data being in the US makes it easier to find additional datasets for enrichment, and through majority vote, it emerged as the top choice among the team's proposed datasets.
Date Agreed | 2026-04-17

## Team Roster
Team Roster
Group 27 · DVN AT3 · Master of Data Science & Innovation · UTS
# | Name | Student No. | Strengths & Skills | Proposed Role | Final Role | Notes | Link to Role Pitch
1 | Ankita Adiveppagouda Patil | 26022830 | Power BI Dev , Data preparation | Artist/Analyst/Data Engineer | Data Visualization | Working on Power BI
2 | Abhishek Chopda | 25611094 | Software Engg & Project Management | Analyst/Orator/Project Architect | Project Co-Manager, Github Manager
3 | Ferdinando Jr Enriquez | 25935343 | Data analysis with Python; Project management across teams; Powerpoint presentations; | Data Engineer / Analyst / Project Manager / Orator | Project Co-Manager
4 | Gem He | 25992948 | EDA and Data Cleaning | Analyst, Data Preparation | Data Engineer (data cleaning), Powerpoint Artist
5 | Harshini Prasad | 26025369 | Model development, software development,power point presesntation | Artist / Architect | Data Visualization
6 | Ka Yan Cheng | 25979218 | Dashboarding | Artist / Analyst | Powerpoint Artist
7 | Ranjan Khanal | 25946613 | Project Management, Project Development, Documentation | Urban Analyst & Architect | Data Engineer (and Visualization)

## Responsibilities (hidden)
Responsibility Matrix
Assign a primary owner and backup for each area.
Responsibility Area | Primary Owner | Backup / Reviewer | Notes
DEVELOPMENT
GitHub / repository management
Code review & quality assurance
ANALYSIS
Data collection & cleaning
Exploratory data analysis
Feature engineering
DESIGN & STRATEGY
Dashboard Design & Branding
User Experience & Narrative Flow
DELIVERABLES
Visualisation / dashboards
Report / written deliverable
Presentation slides
3-min video walkthrough
OPERATIONS
Meeting organiser / facilitator
Minutes & documentation
Final submission upload

## Ways of Working
Ways of Working
Team agreements on tools and processes.
Tool / Area | Platform | Details / Link
Meeting Calls | Microsoft Teams
Game Plan / Task Tracking | Google Sheets
Meeting Notes (raw) | Google Docs
Code Repository | GitHub
File Sharing | Google Drive